## Slide 1: Kaiser Permanente’s Nurse Knowledge Exchange
Chris McCarthy September 2007
chris.mccarthy@kp.org or 510.301.6776

## Slide 2: What the heck is it?
NKE is a system that facilitates smooth, safe, and human-centered shift change
Helps prepare the unit for the arrival of EHR
  Increasing proficiency in PC use
  Pre-Optimizing workflows
Addresses goals for JCAHO 2006

## Slide 3: The Method
Observe & Inquire
Story tell
Synthesize
Brainstorm
Prototype
Field test and implement
Inspire new ideas
Generate new concepts
Test and Refine

## Slide 4: The Project
In January 2004, the four hospital regions (NCAL, SCAL, HI and NW) gathered to begin building the Epic InPatient system. At that first session we asked:
“What processes or workflows in your hospitals do you find challenging?”
The top two responses were:
  Nurse Communications (shift change)
  Bed Management
The four KP HealthConnect alpha sites to lead innovation efforts:
Moanalua
Sunnyside
Baldwin Park
So Sacramento
The goal is to create and implement solutions that are responsive to our providers and members, and help pave the way for & inform KP HealthConnect.

## Slide 5: Nurse Knowledge Exchange
April 2004 Research
May 2004 Storytelling/Brainstorm/Prototype
June 2004 First Implementation

## Slide 6: Research/Storytelling
The need to prepare for the next shift
The oncoming Charge Nurse arrives 30-45 minutes prior to his official shift start time in order to prepare for the oncoming staff. During this time, he gets a “feel for the floor”, confirms staffing plans, organizes the work tasks for oncoming CNAs, and then finally oversees shift report.
“Ghost Town”
Both patients and providers worry about the drop in attention to patient care at shift change time. One patient characterized it as a “ghost town” and many providers said it was chaos, with all the administrative needs having to be taken care of while patient calls ,orders, labs, and other demands continue to pour in.

## Slide 7: Brainstorming
For two-days in May 2004, four-teams of 10 (one from each hospital region) made up of nurses, ward clerks, managers and nurses assistants gathered in Oakland to hear the stories and then brainstorm ideas.
They came up with over 400 ideas!
  Genius Butterfly
  Star Trek communicator
  Arm computer-communicators
  Holographic projectors of location
  Plasma patient info screens

## Slide 8: Prototyping
Before Change
During Change
During Shift
Previous Shift Prep: Outgoing charge nurse or shift leader makes staff assignments for the oncoming nurses.
Patient Care Board: a whiteboard in the patient’s room where daily goals and projected discharge info are written during bedside round. Teach Back
Unit-at-a-Glance: High level overview of patient’s on the unit (similar to Unit system list). Charge RNs or shift leaders use to give handoff to each other.
Bedside Round: Outgoing and oncoming nurses meet at bedside to turnover care. Face-to-face shift change. ISBAR report out
My Brain: printed summary of patient data compiled by nurse for the oncoming nurse. Reviewed by oncoming nurse prior to face-to-face handoff.
The Neuron: An electronic shift change database updated by nurses and unit assistants. Reports from database can be used for exchange of info on the unit and with ancillary services, Bed Control and hospitalists.

## Slide 9: Previous Shift Preparation
The Charge RN or shift leader from the previous shift will make the assignments for the oncoming shift.

## Slide 10: Bedside Round with ISBAR
Oncoming and off-going nurses conduct BEDSIDE ROUNDS during change of shift to ensure a smoother hand-off between nurses.

## Slide 11: Patient Care Board
Patient care goals and upcoming procedures will be noted on whiteboards in the patient rooms to help patients understand their medical journey in the hospital.

## Slide 12: Neuron
A database will be used to help transfer information between nurses. MY BRAIN is the printed report from the NEURON that will give nurses pocket-access to patient information.

## Slide 13: First Implementation
First time I’ve ever made it out here on time. [end of shift]. -RN
I don’t know what’s going on over there (4W), but the nurses seem to love it. – RN from a non-prototype floor
When do we get it?!?!
– RN from a non-prototype floor
The system was tested for two 1-week session in two different hospitals in May 2004.
Three weeks later the first implementation was kicked off in South Sacramento.

## Slide 14: Post-Ideation
Institute for HealthCare Improvement cites NKE as a best practice
Several non-KP hospitals request NKE info
JACHO establishes a 2006 goal that states handoff’s between caregivers should be face to face
  NKE goes way beyond the goal
KP decides to roll out NKE to all KP hospitals using IHI’s Rapid Scale Up method

## Slide 15: Rapid Scale Up Planning (Summer 2005)
Safe, Effective Shift Changes
Process Metrics
NKE as minimum specs
  Shift Prep
  Bedside Rounds
  Structured Report Out
  Goal Board

## Slide 16: Rapid Scale Up (theory)
Unit 1
Unit 2
Unit 3
Unit 5
Unit 4
Unit 6
Unit 7
Unit 8
Unit 9
Unit 10
Unit 12
Unit 11
Unit 13

## Slide 17: Two approaches
Both systems utilized
  InPerson Kickoffs
  Monthly Project Manager Web Calls
  Monthly Team Calls
  1:1 Project Manager Coaching
  Listserves and Extranet
RSUP 1 | RSUP 2
Bottom Up – Hospitals Volunteer to Participate | Top Down – Entire Region Participates
Leadership – local (unit level) | Leadership – Regional/Local
Metric Collection – optional | Metric Collection – required

## Slide 18
2007 - 2008

## Slide 19: Scale Up Insights (2006)
Scale Up is hard work
Success = normalization of process across the system
    Normalization = A process that contains at least the minimum specs that is diffused across the system; a process that looks and feels similar
Leadership is the main factor of success
Compelling, emotional storytelling sets the stage for change (Josey King Story)

## Slide 20: The Beginning
(questions?)