## Slide 1: Metro DC Health Information Exchange (MeDHIX) Characteristics, Challenges, Lessons Learned
Thomas L. Lewis, MD
Leta Kajut, RN, BS, BSN, MHA
Center for Community Based Health Informatics
September 9, 2008

## Slide 2: The Center for Community-Based Health Informatics
Support efforts to achieve greater safety, efficiency, quality, access, and consequently better health care for more people through thoughtful use of health information technology.
Supporting an integrated system of care within clinics using a shared electronic medical record;
Building a health information exchange to share information among safety-net providers and with mainstream health care organizations; and
Fostering partnerships and collaborations among local, regional, and national organizations engaged in similar activities.

## Slide 3: Focus and Goals
Safety net clinics serving low income, uninsured individuals
Community hospitals
Community organizations
Multi-state Health Information Exchange
Many partners
Connect safety net clinics to mainstream health care providers

## Slide 4: Health Care Information Data Flow and Benefits
Quality, Safety, and Efficiency benefits occur at each level
Benefits accrue vertically
Establish Safety Net IT Infrastructure in each clinic
Link Safety Net Clinics Together in cohesive system of care
Link Safety Net Clinics to Mainstream Healthcare

## Slide 5
Metro DC Health Information Exchange
For connecting safety net providers in the Metro DC area
For continuity of care
For sharing data with other providers
Participating clinics in Montgomery County; Washington, DC; Prince Georges County; Northern Virginia
What is MeDHIX?
Notes: <number>
Historically, the PCC has served as an advocate for county residents without insurance or the resources to pay for health care, and has proven to be an efficient administrator of gap-filling programs for Montgomery County. These long-standing programs include Project Access (beginning in 1995), Healthcare for the Homeless (1996), and Care for Kids (1998). Since 2005, the PCC has administered Montgomery Cares, a public/private partnership that is tasked with providing primary and preventive health care to 40,000 low-income, uninsured county adult residents by the year 2010. Montgomery Cares patients receive health services at one of the eight independent nonprofit clinic organizations known collectively as Community HealthLink. In addition, PCC evaluates and obtains significant supplemental funding for these programs, funding that allows for additional programming and enhancements to existing services. Current active PCC grants total $4.25 milliion (December 2007), and include the first-ever Komen Race for the Cure Foundation. Co-recipients with the Primary Care Coalition in this grant are the Montgomery County Department of Health and Human Services and the Uniformed Services University of the Health Sciences.
Within the PCC, the staff is organized into five Centers: the Center for Health Care Access, the Center for Medicine Access, the Center for Community-Based Health Informatics, the Center for Health Improvement, and the Center for Children's Health, each of which is headed by a senior-level director. .

## Slide 6
Enhance patient safety, quality, and efficiency of care
  Share safety net clinic data with hospital emergency departments
  “ED-MC Connect” medical homes identification project
Continuity of care: identify a patient’s medical home
System design that protects patient privacy
Conform to multijurisdictional privacy regulations
Easy to use, web based access
Pertinent information to facilitate care
MeDHIX Care Continuity Goals – Phase 1
Notes: <number>

## Slide 7
CHLCare
Clinic
Clinic
Clinic
Clinic
Clinic
MeDHIX
Clinic
Sub Network Organization
Hospital
Hospital
Current MeDHIX Model
Proxy Server

## Slide 8
Safety Net Clinics
CHLCare
MeDHIX Exchange
Enterprise Service Bus
Routing and Transformation
Data Storage (edge servers
Health Information Exchange
Hospital Emergency Dept’s
Montgomery County, MD
SCC
Langley Park Adults
SCC
Langley Park Peds
Mercy
Peoples
Comm Wellness
Proyecto Salud
Mobile Med
District of Columbia
Virginia Counties
SCC
DC Medical
Arlington
Free Clinic
Laboratory Provider
Hospital A
Hospital B
Hospital C
A Health Information Exchange to link Safety Net clinics to mainstream healthcare
Using CHLCare to make a single connection to MeDHIX, simplifying data exchange
Linking to Quest Diagnostics for Lab Results
MeDHIX is an Information Bridge
Notes: <number>

## Slide 9: CHLCare (EHR) Current Capabilities
Developed collaboratively with safety-net clinics to meet their needs
CHLCare in production since July ’03
Deployed by 15 clinic organizations at over 35 clinic locations
  Montgomery and Prince Georges Counties, DC, Northern Virginia
Prior electronic data converted and added to database
Shared database with 250,000 visit records for 80,000 patients
Content includes
  Patient demographics
  Encounter data, including ICD9 and CPT codes
  Patient appointment scheduling
  Specialty referrals
  Picture ID cards
  Visit planner
  Extensive patient clinical reports and clinic management reports
  Clinical quality assurance data, e.g. diabetes quality measures
  Additional clinical data at the option of individual clinics, e.g. allergies, labs

## Slide 10: MeDHIX Initial Plan: Year 1
“Quick Connect”
  partner with a large regional medical center
  use their proprietary data aggregation and display tools
  accelerate safety net learning and participation
  gain early understanding of benefits and challenges
  CHLCare connection to bring “critical mass” of data quickly
View data using light weight, low cost browser based technology in the safety net clinics
Review and reconcile differing privacy regulations in 3 jurisdictions (Maryland, DC, Virginia)
Develop easily understood data sharing and governance agreements for participating organizations and patients

## Slide 11: MeDHIX Initial Plan: Year 1
Await outcome of ONC NHIN Demonstration Projects to:
  Learn from national efforts
  Use ONC/NHIN standards based technical architecture
  Minimize risk of misdirected expenditures
Explore open source solutions for safety net HIE
Build relationships with regional safety net providers, hospitals, and community organizations
Expand and improve the content of safety net EHRs
Implement at least 1 hospital <-> safety net clinic HIE

## Slide 12: MeDHIX Initial Plan: Year 2
Move from proprietary to standards based infrastructure:
Partner to implement open source solutions for safety net HIE
Expand HIE to two hospital ERs and safety net clinic shared EHR
Assess relative value of data elements to providers
Explore perceptions, barriers, benefits of HIE to various organizations and providers

## Slide 13: MeDHIX Initial Plan: Year 3
Expand HIE to multiple hospital ERs
Expand HIE to include multiple EHRs
Consider HIE with pro bone specialty providers
Assess relative value of data elements to providers
Explore perceptions, barriers, benefits of HIE to various organizations and providers

## Slide 14: MeDHIX Actual Experience: Year 1
Successfully viewed hospital ER data from a safety net clinic using Quick Connect approach
Jointly, with DC Primary Care Association, began a project to choose an EHR for selected DC safety net clinics
Generated substantial interest in the benefits of HIE for safety net populations
Focus on a region wide HIE approach
Good progress on regional privacy understanding

## Slide 15: MeDHIX Year 2: Proof of Principle Meets Reality
Quick Connect partner insisted on thick client
MPI probabilistic match algorithm inadequate for safety net patients
Quick Connect partner sold product to commercial vendor, with complete change in product direction and goals
NHIN prototypes informative but not definitive national model or comprehensive standards
One set of safety net clinics not ready for HIE; focus was on EHR selection and adoption, a multi-year project

## Slide 16: MeDHIX Year 2: Proof of Principle Meets Reality
Community hospitals added new prerequisites for safety net providers for patient identification and HIPAA protection
New project to issue photo IDs to safety net patients
  Meets hospital need for positive patient identification
  Facilitate and authenticate exchange of protected health information
Recurrent legal issues, costs, and lack of consensus concerning patient privacy and access to PHI
  New organizations raise previously resolved issues
  New members of existing organizations revisit old issues
  Delays implementation
  Fear, unwillingness, or excuse not to participate
  Unnecessarily high legal expenses

## Slide 17: MeDHIX Year 2: Proof of Principle Meets Reality
Interest of participants in HIE waxes and wanes
  Other institutional priorities, IT and non-IT related
  Near term needs trump longer term, more hypothetical projects
Stark exemption unintended consequences
  Shifted hospital focus away from regional HIE
  Opportunity to tie physicians to a hospital through EHR subsidy
  Limited resources and competitive pressures undercut HIE
Hospital trust relationships
  Larger competitor institutions not trusted as HIE operator
  Unrelated litigation affected HIE collaboration among hospitals

## Slide 18: MeDHIX Year 2: Proof of Principle Meets Reality
Population-stratified perceived benefits of HIE
  Widely held view that HIE for safety net patients will lead to better quality care and cost reductions. Shared view of hospitals and safety net clinics. (cost/benefit analysis perceived as positive)
  No clear consensus that similar HIE benefits will accrue to insured patients who have strong ties to their personal physicians, smaller numbers of providers, better provider communication of health information, and established HIE methods.
  Risk to privacy perceived as outweighing benefits for cost and quality for insured patients. (risk/benefit analysis not always positive; disclosure may place patients or the hospital at risk)
Closely held clinical information still seen as a competitive advantage by some providers

## Slide 19: MeDHIX Year 2: Proof of Principle Meets Reality
HIE data sharing boundaries
  Comfortable sharing data already being shared
  Reluctant to share data not already being shared
  Preference for role as silent partner in day to day HIE
  Do not want responsibility for managing database inquiries
  Will not permit direct access to their databases
    Vendor contractual constraints
    Firewall management and security concerns and costs
  Unwilling to incur added support costs for HIE without clear benefits
  Willing to incur at most small implementation costs.
Probabilistic matching of patients not accepted
  “Don’t show me data that might not be for this patient”
  “I don’t have time to sort out “possible matches”

## Slide 20: MeDHIX Year 2: Proof of Principle Meets Reality
Clinical data sharing observations
  Safety nets and ERs may differ from other providers
  “Complete” record not necessarily the best
  “eChart synopsis most useful
    Name of clinic providing care
    Patient demographics
    Encounter history, problem list
    Allergies, meds, recent labs, if available
    1 – 2 pages maximum; too much information a deterrent to use
    Discharge summaries of high value to safety net clinics
  Images less useful initially, especially in safety net clinics
Printable eChart most useful in some ER settings
  Ease of integration with ER workflow
  Legal concerns of non-repudiation: “what did you know and when did you know it?”

## Slide 21: MeDHIX Year 2: Proof of Principle Meets Reality
Comprehensive, complex solutions
  May be favored by large institutions
  Unnecessary and inhibiting in smaller settings
  Costly in $, time, and support
    High end graphics work station (thick client)
    Multiple security patches; too much support expertise
    Too much space required
    Most data not needed; too much time to learn
Different providers value clinical data differently
Ease of use vs. complex privacy constraints
  Multiple jurisdictions with conflicting requirements
  Need to document compliance and exceptions easily

## Slide 22: MeDHIX Year 3: Problem Resolution for ER Project
Picture ID Card developed/deployed to safety net patients
  Addresses concerns identified earlier
  Well received by patients and clinics
  Implementation challenges with largely volunteer clinic staff
Open source HIE enterprise service bus architecture tested
Quest laboratory <-> safety net clinic result link deployed
eChart content, design, testing complete
Community hospital ER <-> safety net clinic collaboration defined

## Slide 23: Patient “Dashboard”

## Slide 24
eChart:
  Synopsis of the patient’s medical record
  Web accessible
Picture ID card
Quest electronic laboratory result link
Specific Phase 1 Capabilities

## Slide 25
ID Card
ID Card
Notes: <number>
ID Card demonstrates the intent to share basic medical history electronically between the Primary Care Clinics and Emergency Departments through the MeDHIX eChart – The member ID is also the key to assessing the eChart through the browser.

## Slide 26
Identifies Safety Net Community
Medical Home and Contact Number
Patient Information
CHLCare ID and Indication of Membership in the Health Information Exchange
Disclaimer to insure no misunderstandings' as to the intent of the card occurs
Gender and Date of Birth
Issued Date
Magnetic Swipe contains CHLCare ID
Return to Address
ID Card Design
ID Card

## Slide 27: MeDHIX eChart

## Slide 28
Current Design- Still Evolving
PRIMARY CARE COALITION
Design and Implementation
Notes: <number>

## Slide 29
MeDHIX does not display sensitive data initially
Integrates a process for accessing sensitive data
  Opt in vs. opt out
  Mental health, substance abuse, HIV data
Document successive levels of patient permission
  To access sensitive data
  Hospital policy override (“break the glass”)
Understanding Legal Constraints
Notes: <number>
. MeDHIX also contains a disclaimer in red in the Medications frame in the eChart reminding physicians that Mental Health, Drug Rehab and HIV medications are not displayed and that lack of inclusion does not imply the medications are not currently prescribed to the patient. In addition, there is no alert that some health information has been censored, as that warning in itself would violate a patient’s privacy by identifying that the patient may have a Mental Health, Drug Rehabilitation, or HIV condition.
The legal complexities for data exchange are compounded by the issues that the Community HealthLink consortium has member clinics in Virginia, Maryland and the District of Columbia. The various state statutes must be evaluated and business process adapted to address the data sharing limitations. The phase one MeDHIX implementation employs a three step, “keep it simple” philosophy that does not initially display any data associated with Mental Health, HIV or Drug Rehab. Thus, medications, labs and problem lists associated with these health issues are not displayed in the first eChart view. Consequently, a disclaimer is required on the eChart:
“Data provided may not represent the complete patient history. Confirm all information with the patient and solicit additional information. Mental Health, Drug Abuse and HIV data is not included in eChart as per the following statutes: Virginia: 12.1-127.1; 32.1-36., 27.2-400; District of Columbia: DC Code 7-1201, DC-Code 7-12-2, DC-Code 7-1203; Maryland: Md Code Ann Health Gen 18-338.1, 4-307 Do Not Re-Disclose information as per Virginia Statute 12.1-127.1.03(A)”

## Slide 30
The electronic record is probably not a complete historic depiction of the medical record.
Understanding Legal Constraints
Notes: <number>
A major benefit of MeDHIX is to facilitate patient care by improving access to historical patient information. As a practical matter, MeDHIX membership may not include all the providers who might contribute to the patient’s record. Therefore, data contained in MeDHIX must always be verified with the patient and additional data solicited. The legal complexities for data exchange are compounded by the issues that the Community HealthLink consortium has member clinics in Virginia, Maryland and the District of Columbia. The various state statutes must be evaluated and business process adapted to address the data sharing limitations. Consequently, a disclaimer is required on the eChart:
“Data provided may not represent the complete patient history. Confirm all information with the patient and solicit additional information. Mental Health, Drug Abuse and HIV data is not included in eChart as per the following statutes: Virginia: 12.1-127.1; 32.1-36., 27.2-400; District of Columbia: DC Code 7-1201, DC-Code 7-12-2, DC-Code 7-1203; Maryland: Md Code Ann Health Gen 18-338.1, 4-307 Do Not Re-Disclose information as per Virginia Statute 12.1-127.1.03(A)”

## Slide 31
Sensitive Data Management
Understanding Legal Constraints
Mental Health, Drug Abuse, HIV not displayed
Notes: <number>
. MeDHIX also contains a disclaimer in red in the Medications frame in the eChart reminding physicians that Mental Health, Drug Rehab and HIV medications are not displayed and that lack of inclusion does not imply the medications are not currently prescribed to the patient. In addition, there is no alert that some health information has been censored, as that warning in itself would violate a patient’s privacy by identifying that the patient may have a Mental Health, Drug Rehabilitation, or HIV condition.
The legal complexities for data exchange are compounded by the issues that the Community HealthLink consortium has member clinics in Virginia, Maryland and the District of Columbia. The various state statutes must be evaluated and business process adapted to address the data sharing limitations. The phase one MeDHIX implementation employs a three step, “keep it simple” philosophy that does not initially display any data associated with Mental Health, HIV or Drug Rehab. Thus, medications, labs and problem lists associated with these health issues are not displayed in the first eChart view. Consequently, a disclaimer is required on the eChart:
“Data provided may not represent the complete patient history. Confirm all information with the patient and solicit additional information. Mental Health, Drug Abuse and HIV data is not included in eChart as per the following statutes: Virginia: 12.1-127.1; 32.1-36., 27.2-400; District of Columbia: DC Code 7-1201, DC-Code 7-12-2, DC-Code 7-1203; Maryland: Md Code Ann Health Gen 18-338.1, 4-307 Do Not Re-Disclose information as per Virginia Statute 12.1-127.1.03(A)”

## Slide 32
Sensitive Data Management
Understanding Legal Constraints
Authorization and Consent Recording
Notes: <number>
. MeDHIX also contains a disclaimer in red in the Medications frame in the eChart reminding physicians that Mental Health, Drug Rehab and HIV medications are not displayed and that lack of inclusion does not imply the medications are not currently prescribed to the patient. In addition, there is no alert that some health information has been censored, as that warning in itself would violate a patient’s privacy by identifying that the patient may have a Mental Health, Drug Rehabilitation, or HIV condition.
The legal complexities for data exchange are compounded by the issues that the Community HealthLink consortium has member clinics in Virginia, Maryland and the District of Columbia. The various state statutes must be evaluated and business process adapted to address the data sharing limitations. The phase one MeDHIX implementation employs a three step, “keep it simple” philosophy that does not initially display any data associated with Mental Health, HIV or Drug Rehab. Thus, medications, labs and problem lists associated with these health issues are not displayed in the first eChart view. Consequently, a disclaimer is required on the eChart:
“Data provided may not represent the complete patient history. Confirm all information with the patient and solicit additional information. Mental Health, Drug Abuse and HIV data is not included in eChart as per the following statutes: Virginia: 12.1-127.1; 32.1-36., 27.2-400; District of Columbia: DC Code 7-1201, DC-Code 7-12-2, DC-Code 7-1203; Maryland: Md Code Ann Health Gen 18-338.1, 4-307 Do Not Re-Disclose information as per Virginia Statute 12.1-127.1.03(A)”

## Slide 33
Understanding Legal Constraints
Patient has chosen not to share data

## Slide 34: Stakeholder Concerns Related to Process
Measuring safety, quality, efficiency benefits of HIE difficult
Enthusiasm for HIE; legal, operational, financial concerns
Direction, time course, and benefits of HIE hard to discern
Balancing pressing hospital IT needs with HIE collaboration
ROI clear for hospital IT; ROI speculative for HIE
HIE planning and technology investment substantial

## Slide 35: Hospital Concerns, Limitations, and Constraints
Constraints imposed by existing HIS contracts
  Security
  Prohibition of non-vendor code
  Change in liability/responsibility contract clauses
“Invisible Partner” in HIE
  Need to limit time, resources, cost of HIE participation
Adaptation should be HIE responsibility; little or no change for hospital
Legal liability for privacy/confidentiality breaches
Business risk for privacy/confidentiality breaches

## Slide 36: Stakeholder Observations on the Value of HIE
When it is integrated into day-to-day business processes
  Not an easy or inexpensive task
  Requires considerable staff time and sophistication
When it becomes a standard mechanism for multi-provider communication and care coordination
When data affecting a treatment decision is made available that would not have been known using traditional methods
Value propositions for one organization do not always equate to value for another
The “grand vision” must be coupled to a practical ROI

## Slide 37: Some Final Thoughts about Elephants
A critical mass of clinical data essential for successful HIE
  A special challenge for safety net clinics (staff, $$)
  Limited safety net EHR data -> little or value to hospital or consultants
  No return of discharge summaries or consultant notes -> no value to safety net clinics
Shifting from opt-in to opt-out if legally sound, but is uncomfortable for many organizations
The greatest benefits of HIE are likely to come from both individual and system wide practice re-design, not from HIE itself.

## Slide 38
Too Many RHIOs?
National Capital Area RHIO (DC RHIO)
Pediatric Regional Health Information Network
DC Medicaid Transformation Grant
INOVA EHR activities and regional implications
Northern Virginia RHIO
NOVA Scripts Central
DC Primary Care Association EHR Project
Regional Health Information Technology Activities
Notes: <number>
Historically, the PCC has served as an advocate for county residents without insurance or the resources to pay for health care, and has proven to be an efficient administrator of gap-filling programs for Montgomery County. These long-standing programs include Project Access (beginning in 1995), Healthcare for the Homeless (1996), and Care for Kids (1998). Since 2005, the PCC has administered Montgomery Cares, a public/private partnership that is tasked with providing primary and preventive health care to 40,000 low-income, uninsured county adult residents by the year 2010. Montgomery Cares patients receive health services at one of the eight independent nonprofit clinic organizations known collectively as Community HealthLink. In addition, PCC evaluates and obtains significant supplemental funding for these programs, funding that allows for additional programming and enhancements to existing services. Current active PCC grants total $4.25 milliion (December 2007), and include the first-ever Komen Race for the Cure Foundation. Co-recipients with the Primary Care Coalition in this grant are the Montgomery County Department of Health and Human Services and the Uniformed Services University of the Health Sciences.
Within the PCC, the staff is organized into five Centers: the Center for Health Care Access, the Center for Medicine Access, the Center for Community-Based Health Informatics, the Center for Health Improvement, and the Center for Children's Health, each of which is headed by a senior-level director. .

## Slide 39
Too Many RHIOs?
Maryland Governor’s HIT Advisory Committee Report
Maryland Citizen-Centric Health Information Exchange
Maryland statewide HIE plan
PCC AHRQ funded MeDHIX project
Maryland Community Health Centers EHR plans
PCC Montgomery County EHR Assessment Activities
Regional Health Information Technology Activities
Notes: <number>
Historically, the PCC has served as an advocate for county residents without insurance or the resources to pay for health care, and has proven to be an efficient administrator of gap-filling programs for Montgomery County. These long-standing programs include Project Access (beginning in 1995), Healthcare for the Homeless (1996), and Care for Kids (1998). Since 2005, the PCC has administered Montgomery Cares, a public/private partnership that is tasked with providing primary and preventive health care to 40,000 low-income, uninsured county adult residents by the year 2010. Montgomery Cares patients receive health services at one of the eight independent nonprofit clinic organizations known collectively as Community HealthLink. In addition, PCC evaluates and obtains significant supplemental funding for these programs, funding that allows for additional programming and enhancements to existing services. Current active PCC grants total $4.25 milliion (December 2007), and include the first-ever Komen Race for the Cure Foundation. Co-recipients with the Primary Care Coalition in this grant are the Montgomery County Department of Health and Human Services and the Uniformed Services University of the Health Sciences.
Within the PCC, the staff is organized into five Centers: the Center for Health Care Access, the Center for Medicine Access, the Center for Community-Based Health Informatics, the Center for Health Improvement, and the Center for Children's Health, each of which is headed by a senior-level director. .

## Slide 40
Tom Lewis
  tom_lewis@primarycarecoalition.org
  301-628-3418
Leta Kajut
  leta_kajut@primarycarecoalition.org
  301-628-3429
Charity Dorazio
  Charity_dorazio@primarycarecoalition.org
  301-628-3411
Guy Fisher
  Guy_fisher@primarycarecoalition.org
  301-628-3423
Contact Information
Notes: <number>