## Slide 1
Lessons learned:
Implementing a low-cost structure
Health Information Exchange
Agency for Healthcare Research & Quality
September 8, 2008
Frank Richards
Chief Information Officer
Geisinger Health System

## Slide 2
Geisinger Health System
Danville, PA
Notes: Picture of the Geisinger Medical Center complex in Danville, PA, the main campus of the Geisinger Health System.

## Slide 3: About the Geisinger Health System
Founded in 1915, the Geisinger Health System is an integrated delivery system including hospitals, clinics and an insurance company serving Northeast and North Central Pennsylvania.
4 Inpatient Facilities
Service area - 2.6 million residents
Serves 43 of PA’s 67 counties
700 employed physicians & 270 Residents
41 community practice sites; ~200 primary care physicians
Approximately 2 million outpatient visits per year
Rural and aging population
Tertiary/quaternary care medical centers and specialty hospitals
Insurance Operations - Covers 220,000 lives

## Slide 4
CENTRE COMMUNITY HOSP.
LEWISTOWN HOSP.
MOSES TAYLOR HOSPTAIL
POTTSVILLE HOSPITAL
TYLER MEMORIAL HOSPITAL
LOCK HAVEN HOSP.
BLOOMSBURG HOSP.
SUNBURY COMM. HOSP.
GOOD SAMARITAN HOSP.
COMMUNITY MEDICAL CTR.
PHILLIP[SBURG AREA HOSP.
CLEARFIELD HOSPITAL
SHAMOKIN AREA HOSP.
MERCY HOSPITAL SCRANTON
Notes: Graphic of Pennsylvania showing counties in the Geisinger system’s service area. Major Clinical hubs are designated with large stars. Smaller Geisinger clinic sites are designated with red stars.

## Slide 5: Geisinger’s Electronic Health Record (EHR)
Major investments over 10 years in electronic health records.
Implemented a full ambulatory EHR system-wide by 2002.
Began providing access to referring providers and patients in 2000.
Currently have over 250 non-Geisinger practices on-line
Over 100,000 patients on-line

## Slide 6: What is KeyHIE?
Keystone Health Information Exchange – a group of provider organizations that believed broader access to clinical information could improve care
Started with a survey of 53 hospitals in northeast and central Pennsylvania
Initial meeting of 20 interested organizations
Ongoing group of 7 healthcare organizations, including a medium sized physician group
Subgroup of 3 organizations that initially implemented technology for the Exchange.

## Slide 7
KeyHIE Milestones
2004 AHRQ Planning Grant
2005 Regional Survey / Symposium
2005 AHRQ Implementation Grant
2005 MOU to establish Central Penn Health Information Collaborative (CPHIC)
2007 PA Dept of Health Grants
2007 Renamed to KeyHIE be more inclusive

## Slide 8
31 counties
53 hospitals
9,000 physicians
2.6 million residents
KeyHIE Proposed Service Area
Notes: Map of Pennsylvania showing the Keystone Health Information Exchange’s proposed service area. IT consists of 31 counties in northeastern and central Pennsylvania.

## Slide 9: Participants for the AHRQ Grant
* Replaced Sunbury Community Hospital in 2005
*
Notes: Slide shows the logos of the KeyHIE organizations participating in the AHRQ grant.

## Slide 10: Participants for the AHRQ Grant
Shamokin Area Community Hospital
70 Beds 27 Active Staff Phys 342 Employees (4 FTE’s in IT, incl mgr)
Bloomsburg Hospital
72 Beds 64 Active Staff Phys 317 Employees (7 FTE’s in IT, incl mgr)
Geisinger Health System
917 Beds (4 Inpatient Facilities) 700 Employed Physicians (plus non-Geisinger physicians) 14,000 Employees (520 FTE’s in IT)

## Slide 11: Goals
Improve quality of care and patient safety (regardless of which partner's services the patient may be accessing).
Provide basic clinical information services.
Improve communication among patients, practices, and hospitals.
Provide access to an expanding set of HIT services--including a high-performance EHR--which would not otherwise be available.
Improve local practice and hospital viability.
Meet project time frame and budget constraints.

## Slide 12: Approach
Initially researched products to permit storage of information in a common format. Discarded due to cost.
Developed an approach to leverage existing technologies.
  Existing Patient Index
  Existing Clinical Information Systems at each organization
Developed a portal to access the information residing in the disparate systems.
Start in the EDs as a proof of concept to show value of information sharing where lack of information can be most acute.

## Slide 13: Challenges
Ability to identify patients reliably across multiple information systems.
Financial incentives do not encourage information sharing.
Concerns about information ownership.
How do we pay for this? Access to capital limited for rural healthcare providers.

## Slide 14: Challenges
Coordinated planning may be difficult due to lack of regular, face-to-face contact among rural hospitals and providers.
Small and financially vulnerable rural providers may tend to feel threatened by provider organizations large enough to have the resources necessary to be helpful.
Rural providers may have fewer organization-change skills than other providers.
Concerns about the privacy and confidentiality of patients' information.

## Slide 15
Example Architecture Information Sharing
CMPI:
Patient Name
DOB
MRN(n)
Address
Phone#
Auth
Registration
Org. C
Registration
Org. B
Registration
Org. A
Chart Locator:
Patient
Site
Provider
DOS,
Enc Type
Dx
Data Population Model
Data Retrieval Model
User Portal
Results Viewer
Org. C
Results Viewer
Org. B
Results Viewer
Org. A
User Authentication
Activity Log
Notes: High-level diagram of the KeyHIE information exchange showing registration flows, master patient index and chart locator service on the left. And user portal and authentication, and data retrieval on the right. The diagram depicts an architecture where patient encounter lists are built via registration interfaces from the participating organizations, and information is retrieved via a portal that supports single sign-on to each organization’s system.

## Slide 16: Year 1 Objectives & Deliverables
OBJECTIVES
Develop grant admin & measurement tools
Install Master Patient Index across pilots…
Complete lab interfaces…………………...
Phase 1 portal deployed…………………..
Develop regional governance…………….
DELIVERED

Partial
Not completed



## Slide 17: Year 1 Findings
Community hospital resource constraints
  Limited resources, especially IT staff
  Local vs. Shared Priorities
Hospital management turnover can affect project commitments. (e.g., Sunbury Community Hospital)
Larger organization needs to take more of the lead.

## Slide 18: Year 2 Objectives & Deliverables
OBJECTIVES
Install Master Patient Index across pilots…
Complete lab interfaces…………………...
Phase 2 portal deployed…………………..
Phase 3 portal deployed
Expand regional governance……………..
DELIVERED

partial


No

## Slide 19: Year 2 Findings
Additional funding available from PA Dept of Health
  Provide regional LOINC education
  Deploy single sign-on for Exchange
First lab site interface operational – requires an ongoing support model
Funding needed for non-IT services (e.g., legal services to develop Bloomsburg Hospital access agreement)
Collecting patient authorizations for participation was a rate limiting factor to access of information and adoption
Combined phase 2 portal with phase 3 – still limited use
NEPA-RHIO disbanded

## Slide 20: Year 3 Objectives & Deliverables
DELIVERED
Partial
Underway
Underway
Ongoing
OBJECTIVES
Expand Exchange portal throughout region………………………………
Deploy document store……………
Complete evaluation………………
Expand regional governance………

## Slide 21: Year 3 Findings
Increased usage is occurring, although the need to navigate multiple systems is still a barrier.
The document store is expected to address many of the issues of needing to access multiple systems
Real-time events such as transfers or consults may be the first compelling business case for data exchange.
There is still some skepticism about test results external to one’s own organization
Everything costs more, takes more effort than first planned

## Slide 22
Smith, Bob
Notes: Screen shot of the KeyHIE system showing how patient information is displayed for the various sites.

## Slide 23
Smith, Bob
Notes: Screen shot of the KeyHIE system showing how patient information is displayed for the various sites and a sub-screen encounters showing the encounters the patient has had at each organization.

## Slide 24: Lessons Learned
Small hospitals have a difficult time providing even minimal time to efforts outside their immediate domain.
The need to share information for care and respect patients’ privacy is an ongoing challenge.
Use of any system must be integral to the care process.
Leadership and commitment are key to accomplishing anything.

## Slide 25: Discussion
This project was supported by grant number UC1HS016162 from the Agency for Healthcare Research and Quality, and in part,
under a contract with the Pennsylvania Department of Health. Basic data for use in this study were supplied by the Pennsylvania
Department of Health, Harrisburg, Pennsylvania. The department specifically disclaims responsibility for any analysis,
interpretations or conclusions. Edward G. Rendell, GOVERNOR.