## Slide 1: Improving Patient Flow and Reducing Emergency Department Crowding An Evaluation of Interventions at Six Hospitals AHRQ Annual Meeting September 27, 2010
Megan McHugh, HRET Kevin Van Dyke, HRET Julie Yonek, Northwestern University Embry Howell, Urban Institute Fiona Adams, Urban Institute
Notes: <number>

## Slide 2: The Problem
Half of hospitals report operating at or above capacity (AHA 2007).
A minority of hospitals meet recommended wait times for all ED patients (Horwitz et. al. 2009).
Approximately 500,000 ambulances are diverted each year (Burt et. al. 2006).
On a “typical” Monday, 73% of EDs are boarding two or more admitted patients (Schneider et. al. 2003).
Notes: <number>
<number>

## Slide 3: The Consequences
Increased door-to-needle times for patients with suspected acute myocardial infarction (Schull et. al. 2004)
Lower likelihood of patients with community-acquired pneumonia to receive timely antibiotic therapy (Fee et. al. 2007, Pines et. al. 2007)
Poor pain management (Hwang et. al. 2008)
Increased mortality (Richardson et. al. 2006, Sprivulis et. al. 2006)
Lower patient and staff satisfaction (Boudreaux et. al. 2004, Richards et. al. 2000)
Notes: <number>
<number>

## Slide 4: Research Questions
What factors facilitated or hindered the implementation of strategies?
What resources were used to implement the strategies, and what was the associated cost?
What changes in patient flow occurred after the implementation of the strategies?
Notes: <number>
<number>

## Slide 5: Urgent Matters Learning Network (UMLN)
Notes: <number>
<number>

## Slide 6: UMLN Hospital Requirements
Form a multi-disciplinary, hospital-wide team
Select and implement improvement strategies
Complete an implementation plan and monthly progress reports
Participate in UMLN meetings
Participate in the evaluation of the strategies
Notes: <number>
<number>

## Slide 7: UMLN Framework
Notes: <number>
<number>

## Slide 8: UMLN Interventions
Protocols for specialty consultations
Standardized registration and triage
Mid-Track
ED/Inpatient department communication tool
ESI Five-level triage
Immediate bedding
Fast track improvement (2 hospitals)
Notes: <number>
<number>

## Slide 9: Methods – Data & Analysis
Two rounds of interviews (129 total)
  Recorded, transcribed, uploaded to Atlas
  Grounded theory approach
  “Ingredient” approach
Patient-level data:
  Pre-Implementation (Dec 08 – Feb 09)
  Post-Implementation (Dec 09 – Feb 10)
  Dependent variables: ED LOS, LWBS
  Independent variables: Date/time of visit, age, gender, triage level, lab, x-ray, disposition, occupancy rate
Notes: <number>
<number>

## Slide 10: Common Facilitators/Barriers to Implementation
Facilitators:
  Participation in UMLN
  Executive support/availability of resources
  Strategic selection of planning team
Barriers:
  Staff resistance
  Organizational culture
  Lack of staff resources
Notes: <number>
<number>

## Slide 11: Implementation Expenses
Strategy | Description of Expense | Total Expense
Fast track improvement (1) | Construction project 3 Nurse practitioners | $490,000
Mid-Track | Construction project GYN stretcher EM physician | $320,683
Registration & triage | Computers on wheels Triage training | $32,850
ED/Inpatient Communication | Fax machine | $200
No new resources were acquired for the following strategies:
Fast track improvement (2), Protocols for specialty consults, ESI Five-level triage, Immediate bedding
Notes: <number>
<number>

## Slide 12: Hours Spent Planning and Implementing
Position | Hours
ED nurses | 963
ED charge nurses/Nurse educators | 680
ED technicians | 352
Physician specialists | 315
Process/quality improvement leaders | 280
ED administrative directors | 271
ED nurse managers | 238
Registration managers | 108
Notes: <number>
<number>

## Slide 13: Hours Spent Planning and Implementing
Strategy | Total Hours
Immediate bedding | 40
Mid-Track | 65
Fast track improvement (1) | 160
ED/Inpatient communication tool | 239
Protocols for specialty consultations | 256
Fast track improvement (2) | 371
Standardized registration & triage | 857
ESI Five-Level triage | 1,017
Notes: <number>
<number>

## Slide 14: Hours Spent Planning and Implementing
Position | Hours
ED physicians | 107
Inpatient unit floor managers | 100
ED department chairs/physician directors | 87
Hospital c-suite | 59
ED nurse practitioner/physicians assistants | 49
Hospital director-level | 32
Data/IT analysts | 13
ED clerks | 5
Notes: <number>
<number>

## Slide 15: Change in ED Length of Stay
LOS in Minutes
Regression-Adjusted Mean ED Length of Stay,
Pre and Post Implementation
Notes: The interventions displayed above were associated with a significant reduction in ED LOS at the p<.05 level. Data are shown for all ED patients, except Mid-Track, which includes data for ESI III s only. All other interventions were not found to be significantly associated with a reduced ED LOS.
Notes: <number>
<number>

## Slide 16: Lessons for Other Hospitals
Leverage factors that facilitate implementation.
Develop a plan to address challenges early.
Recognize that some strategies require significant financial and/or time investment.
Recognize the important roles played by non-MDs and RNs (e.g., registrars, clerks, techs).
The effort may result in statistically significant and meaningful improvements in patient flow.
Notes: <number>
<number>

## Slide 17: http://www.urgentmatters.org Megan McHugh, PhD Director, Research Health Research & Educational Trust American Hospital Association mmchugh@aha.org
Notes: <number>