## Slide 1: Project RED: Module 1
Preparing to Redesign Your Discharge Program
Notes: <number>
Project RED: Module 1
Preparing for the redesign of your discharge program

## Slide 2: Re-Engineering Discharge Project RED
The goal of this self-learning course is to help hospitals across the country implement Project RED
Project RED improves the discharge process to assist patients more safely care for themselves at home and to prevent readmissions
Notes: Re-Engineering Discharge Project RED
The goal of this self-learning course is to help hospitals across the country implement Project RED
Project RED improves the discharge process to assist patients more safely care for themselves at home and to prevent readmissions

## Slide 3: Module 1 Outline
Course overview modules 1-4
Strategic priorities
Performance improvement structure
Role clarification
Systematic PI process
Project RED components
Notes: Module 1 Outline
Course overview modules 1-4
Strategic priorities
Performance improvement structure
Role clarification
Systematic PI process
Project RED components

## Slide 4: Participant’s Training Program: A Facilitated Implementation Plan
General information and strategies for designing and implementing improvement processes over time
Information on how to operationalize specific discharge planning processes
A comprehensive systematic performance improvement project plan that will include timelines and strategies for use immediately following completion of the four-module program
Notes: Participant’s Training Program: Facilitated Implementation Plan
General information and strategies for designing and implementing improvement processes over time
Information on how to operationalize specific discharge planning processes
A comprehensive systematic performance improvement project plan that will include timelines and strategies for use immediately following completion of the four-module program

## Slide 5: Discharge Planning
Patient Admission
H & P
Rx Plan
PATIENT EDUCATION
Discharge Order Written
Discharge Process
Discharge Event
DISCHARGE INSTRUCTIONS
Post-D/C Follow-up
Notes: Discharge Planning
Image: Graphic of discharge planning with patient education and discharge instructions as the foundation.

## Slide 6: Course Overview Modules 1- 4
Module 1 – Getting started
Module 2 – Patient admission
care and treatment
Module 3 – Patient discharge and follow-up care
Module 4 – Preparing to launch
Notes: Course Overview Modules 1- 4
Module 1 – Getting started
Module 2 – Patient admission care and treatment
Module 3 – Patient discharge and follow-up care
Module 4 – Preparing to launch

## Slide 7: Module 1: Objectives
Identify organizational strategic priorities that will align with local, regional, and national requirements
Develop a systematic performance improvement process to facilitate knowledge transfer and sustainable change
Review the roles of executive sponsor, project team leader, discharge advocate, physician champion, and pharmacist in the redesigned discharge process
Develop an understanding of Project RED’s 11 components
Notes: <number>
Module 1: Objectives
Identify organizational strategic priorities that will align with local, regional, and national requirements
Develop a systematic performance improvement process to facilitate knowledge transfer and sustainable change
Review the roles of executive sponsor, project team leader, discharge advocate, physician champion, and pharmacist in the redesigned discharge process
Develop an understanding of Project RED’s 11 components

## Slide 8: Strategic Priorities
Improve patient outcomes
Improve cost/revenue management
Improve HCAHPS scores
Prepare for changes to CMS reimbursement penalties for high readmission rates
Improve nurse/provider time utilization
Enhance portability of PHI across the continuum of care
Improve relationship with PCPs
Notes: <number>
Strategic Priorities Improve patient outcomes
Improve cost/revenue management
Improve HCAHPS scores
Prepare for changes to CMS reimbursement penalties for high readmission rates
Improve nurse/provider time utilization
Enhance portability of PHI across the continuum of care
Improve relationship with PCPs
<number>

## Slide 9
Explicit delineation of roles and responsibilities
Discharge process initiation upon admission
Patient education throughout hospitalization
Timely accurate information flow:
From PCP ► Among hospital team ► Back to PCP
Complete patient discharge summary prior to discharge
Principles of the Re-Engineered Hospital Discharge
Notes: <number>
<number>
Principles of the Re-Engineered Hospital Discharge
Explicit delineation of roles and responsibilities
Discharge process initiation upon admission
Patient education throughout hospitalization
Timely accurate information flow:
From PCP ► Among hospital team ► Back to PCP
Complete patient discharge summary prior to discharge
<number>

## Slide 10
Comprehensive written discharge plan provided to patient prior to discharge
Discharge information in patient’s language and literacy level
Reinforcement of plan with patient after discharge
Availability of case management staff outside of limited daytime hours
Continuous quality improvement of discharge processes
Principles of the Re-Engineered Hospital Discharge
(continued)
Notes: <number>
<number>
Principles of the Re-Engineered Hospital Discharge continued
Comprehensive written discharge plan provided to patient prior to discharge
Discharge information in patient’s language and literacy level
Reinforcement of plan with patient after discharge
Availability of case management staff outside of limited daytime hours
Continuous quality improvement of discharge processes
<number>

## Slide 11: Performance Improvement Structure
Deming, Shewhart, Lean
Plan
Do
Check (Study)
Act
Lean Six Sigma
Define
Measure
Analyze
Improve
Control
Notes: Performance Improvement Structure
Deming, Shewhart, Lean
Plan
Do
Check (Study)
Act
Lean Six Sigma
Define
Measure
Analyze
Improve
Control

## Slide 12: Determine Your Infrastructure
Oversight Committee
Champion
Project Team
Champion
Project Team
Project Team
Project Team
Notes: Six Sigma Forum, Post Conference Workshop
May 30, 2008
www.ies.ncsu.edu/leanhealthcare
<number>
Determine Your Infrastructure
Diagram of Hierarchy with Oversight Committee at the top, Champion in the middle, and Project Team on the bottom.

## Slide 13: Project RED Oversight Committee - Steering
Vision
Mandate improvement
Identify champions
Receive and review updates
Notes: Six Sigma Forum, Post Conference Workshop
May 30, 2008
www.ies.ncsu.edu/leanhealthcare
<number>
Project RED Oversight Committee – Steering
Vision
Mandate improvement
Identify champions
Receive and review updates

## Slide 14: Emphasize Process, Focus on Results
What really matters to the organization? Achieve bottom-line results
Can we measure the impact of the project?
How much has the project contributed this year and will contribute in future years?
Notes: Six Sigma Forum, Post Conference Workshop
May 30, 2008
www.ies.ncsu.edu/leanhealthcare
<number>
Emphasize Process, Focus on Results
What really matters to the organization? Achieve bottom-line results
Can we measure the impact of the project?
How much has the project contributed this year and will contribute in future years?

## Slide 15: Project Champion
Communicates the vision
Selects project and scope
Selects candidates for training
Reviews projects weekly
Removes barriers and supplies resources
Notes: Six Sigma Forum, Post Conference Workshop
May 30, 2008
www.ies.ncsu.edu/leanhealthcare
<number>
Project Champion
Communicates the vision
Selects project and scope
Selects candidates for training
Reviews projects weekly
Removes barriers and supplies resources

## Slide 16: The Project Team
Leader
Physician champion
Discharge advocate
Patient’s physician
Pharmacist
Notes: Six Sigma Forum, Post Conference Workshop
May 30, 2008
www.ies.ncsu.edu/leanhealthcare
<number>
The Project Team
Leader
Physician champion
Discharge advocate
Patient’s physician
Pharmacist

## Slide 17: Project Team Leader
Becomes educated in PI tools
Is a competent and confident facilitator
Is objective and neutral to the process
Facilitates an organized plan for the team
Is results focused
Notes: Six Sigma Forum, Post Conference Workshop
May 30, 2008
www.ies.ncsu.edu/leanhealthcare
<number>
Project Team Leader
Becomes educated in PI tools
Is a competent and confident facilitator
Is objective and neutral to the process
Facilitates an organized plan for the team
Is results focused

## Slide 18: Project Physician Champion
Communicates with senior leaders
Communicates with medical staff
Provides physician perspective to the project team
Assists in the elimination of system barriers
Believes in the Project RED intervention and value of improving discharge program
Notes: Project Physician Champion
Communicates with senior leaders
Communicates with medical staff
Provides physician perspective to the project team
Assists in the elimination of system barriers
Believes in the Project RED intervention and value of improving discharge program
<number>

## Slide 19: Discharge Advocate
Designed to oversee patient discharge preparation
Coordinates all discharge activities within patient population
Facilitates team activities and discharge planning rounds with primary MD
Collects discharge focused data
Ensures completion of discharge plan and demonstrated learning by the patient
Notes: Discharge Advocate
Designed to oversee patient discharge preparation
Coordinates all discharge activities within patient population
Facilitates team activities and discharge planning rounds with primary MD
Collects discharge focused data
Ensures completion of discharge plan and demonstrated learning by the patient
<number>

## Slide 20: Discharge Advocate
Is notified when patients in target population are admitted/diagnosed
Initiates action steps associated with Project RED
Initiates Patient Care Plan
Educates patient and family about condition, medications, other treatments, post-discharge plans, and follow up ordered by the physician
Reviews plan with patient and family
Collects measurement data specific to project and patient population
Notes: Discharge Advocate
Is notified when patients in target population are admitted/diagnosed
Initiates action steps associated with Project RED
Initiates Patient Care Plan
Educates patient and family about condition, medications, other treatments, post-discharge plans, and follow up ordered by the physician
Reviews plan with patient and family
Collects measurement data specific to project and patient population

## Slide 21: Patient’s Physician
Initiates patient plan of care based on critical pathway
Leads and/or participates in discharge planning rounds
Communicates potential date of discharge
Supports the performance improvement process
Notes: Patient’s Physician
Initiates patient plan of care based on critical pathway
Leads and/or participates in discharge planning rounds
Communicates potential date of discharge
Supports the performance improvement process

## Slide 22: Pharmacist
Verifies physician orders
Reconciles admission medications with medications from home
Collaborates with care team specific to discharge needs
Reconciles medications upon discharge
Assists with patient medication questions
Notes: Pharmacist
Verifies physician orders
Reconciles admission medications with medications from home
Collaborates with care team specific to discharge needs
Reconciles medications upon discharge
Assists with patient medication questions

## Slide 23: As a Team, Answer the Following Questions
Is our project scope manageable?
Do we have PI structure including oversight steering committee; project champion; DA; pharmacist; team members; team leader; scheduled dates, times, and resources needed for the meetings?
Have we alerted ad hoc resources such as finance, medical records, IT, education dept, etc., as needed?
What is missing and who will be responsible?
Notes: As a Team, Answer the Following Questions
Is our project scope manageable?
Do we have PI structure including oversight steering committee; project champion; DA; pharmacist; team members; team leader; scheduled dates, times, and resources needed for the meetings?
Have we alerted ad hoc resources such as finance, medical records, IT, education dept, etc., as needed?
What is missing and who will be responsible?
<number>

## Slide 24: Develop the Team Charter
Establish team members
Identify key stakeholders
Determine the problem statement
Determine the AIM statement (mission)
Identify patient and organizational benefits
Establish project targets and milestones
Acquire senior leadership sanctioning
Notes: Develop the Team Charter
Establish team members
Identify key stakeholders
Determine the problem statement
Determine the AIM statement (mission)
Identify patient and organizational benefits
Establish project targets and milestones
Acquire senior leadership sanctioning

## Slide 25: Sample Team Charter
Notes: Sample Team Charter
Table: Table gives an example of a team charter.

## Slide 26: Define the Current State
Initiate a high-level process map
Multidisciplinary participation
Patient admission is the starting point
After hospital care provision is the ending point
Ask each discipline what steps it takes to prepare the patient for discharge
Notes: Define the Current State
Initiate a high-level process map
Multidisciplinary participation
Patient admission is the starting point
After hospital care provision is the ending point
Ask each discipline what steps it takes to prepare the patient for discharge

## Slide 27: Your Current State May Look Like This
Notes: Your Current State May Look Like This
Graphic: Process flow image identifying the steps in between admission and patient discharge

## Slide 28
Notes: Sample Process Map: Patient Discharge
Graphic: Image of swim lane diagram, identifying specific steps by role: Physician, Nurse, DA, Pharmacist
<number>

## Slide 29: Once the Process Map is Completed
Analyze the work flow in the eyes of the patient
What defects exist? Where are communication breakdowns, failure to hand off information?
Where do delays occur?
What are your Project RED gaps?
Do we have omission , selection, documentation, communication, administration failures?
What steps in this process would the patient be willing to “pay for”?
Notes: Once the Process Map is Completed
Analyze the work flow in the eyes of the patient
What defects exist? Where are communication breakdowns, failure to hand off information?
Where do delays occur?
What are your Project RED gaps?
Do we have omission , selection, documentation, communication, administration failures?
What steps in this process would the patient be willing to “pay for”?
<number>

## Slide 30: Establish Your Gap Analysis
Sample Current State Process
Discharge order
Discharge instruction form
Discharge teaching on day of discharge
No discharge advocate
No appt scheduled
No post DC phone call
No PCP DC Summary
Project RED Components
Med reconciliation
National guideline used
Follow-up appointment
Outstanding tests
Post DC services
Written DC care plan
Emergency contact
Patient education
Demonstrated learning
DC summary to PCP
Post DC phone call
Notes: Establish Your Gap Analysis
Sample Current State Process
Discharge order
Discharge instruction form
Discharge teaching on day of discharge
No discharge advocate
No appt scheduled
No post DC phone call
No PCP DC Summary
Project RED Components
Med reconciliation
National guideline used
Follow-up appointment
Outstanding tests
Post DC services
Written DC care plan
Emergency contact
Patient education
Demonstrated learning
DC summary to PCP
Post DC phone call
<number>

## Slide 31: Challenges to Implementation: Medical Team Related
Busy medical team means discharge receives low priority in the work schedule of inpatient clinicians
Discharge is relegated to least-experienced team member
Last-minute tests/consultations result in delay of final discharge plan and medication list
Inaccurate medication reconciliation
Discharge medication reconciliation started on the day of discharge
Notes: <number>
<number>
Challenges to Implementation: Medical Team Related
Busy medical team means discharge receives low priority in the work schedule of inpatient clinicians
Discharge is relegated to least-experienced team member
Last-minute tests/consultations result in delay of final discharge plan and medication list
Inaccurate medication reconciliation
Discharge medication reconciliation started on the day of discharge

## Slide 32: Challenges to Implementation: Hospital Related
Lack of resources and financial incentives to sustain discharge programs
Standardized discharge papers are not personalized or in patient’s language
Resistance to change by clinicians
Financial pressure to fill beds as soon as they are empty
Notes: Challenges to Implementation: Hospital Related Lack of resources and financial incentives to sustain discharge programs
Standardized discharge papers are not personalized or in patient’s language
Resistance to change by clinicians
Financial pressure to fill beds as soon as they are empty

## Slide 33: Challenges to Implementation: Patient Related
Patient with no PCP
Limited or no insurance coverage
Inability to pay for medication co-pays
Long wait times when calling health centers
Late discharge is less effective because staff are teaching patients who are anxious to leave
Notes: <number>
Challenges to Implementation: Patient Related
Patient with no PCP
Limited or no insurance coverage
Inability to pay for medication co-pays
Long wait times when calling health centers
Late discharge is less effective because staff are teaching patients who are anxious to leave
<number>

## Slide 34
Notes: Image: Graphic image of fishbone diagram, analyzing the causes for patient readmission, including materials, discharge process, communication, people
<number>

## Slide 35: Process Metrics
Average time to notify DA about new admission
Average time from admission to first patient visit by DA (initiation of care plan) – only for patients who meet all criteria
Percent of patients’ PCPs notified within 24 hours discharge
Percent of follow-up phone calls made within 48 hours
Percent of follow-up calls requiring second call by pharmacist (if non-pharmacist makes first call)
Percent of patients completing post-discharge survey (30 days after discharge)
Notes: <number>
<number>
<number>
Process Metrics
Average time to notify DA about new admission
Average time from admission to first patient visit by DA (initiation of care plan) – only for patients who meet all criteria
Percent of patients’ PCPs notified within 24 hours discharge
Percent of follow-up phone calls made within 48 hours
Percent of follow-up calls requiring second call by pharmacist (if non-pharmacist makes first call)
Percent of patients completing post-discharge survey (30 days after discharge)

## Slide 36: Process Metrics
Completion of care plan details
  Percent of care plans with medication list included
  Percent of care plans with care needs included (e.g., exercise, diet, main problem, when to call doctor)
  Percent of care plans with follow-up appointments listed
  Percent of care plans with pre-arranged discharge resources identified (e.g., home health, durable medical equipment)
  Percent of care plans with pending tests listed
Notes: <number>
<number>
<number>
Process Metrics
Completion of care plan details:
  Percent of care plans with medication list included
  Percent of care plans with care needs included (e.g., exercise, diet, main problem, when do I call doctor)
  Percent of care plans with follow-up appointments listed
  Percent of care plans with pre-arranged discharge resources identified (e.g., home health, durable medical equipment)
  Percent of care plans with pending tests listed

## Slide 37: Outcome Metrics for Target Population
Average length of stay
30-day unplanned all-cause readmission rate
The cost of second LOS (readmission)
Pre/post data: Patient experience related to discharge preparation
Pre/post data: Frontline staff survey related to discharge preparation
Notes: Outcome Metrics for Target Population
Average length of stay
30-day unplanned all-cause readmission rate
The cost of second LOS (readmission)
Pre/post data: Patient experience related to discharge preparation
Pre/Post data: Frontline staff survey related to discharge preparation
<number>

## Slide 38: Let Us Pause A Moment
Discuss high-level process map comparison
Determine when you will draw/redraw your high-level map
What failures are you predicting?
What measurements do you have in place?
Notes: Let Us Pause A Moment
Discuss high-level process map comparison
Determine when you will draw/redraw your high-level map
What failures are you predicting?
What measurements do you have in place?
<number>

## Slide 39: RED Checklist
Eleven mutually reinforcing components:
1. Medication reconciliation
2. Reconcile discharge plan with national guidelines
3. Follow-up appointments
4. Outstanding tests
5. Post-discharge services
6. Written discharge plan
7. What to do if problem arises
8. Patient education
9. Assess patient understanding
10. Discharge summary sent to PCP
11. Telephone reinforcement
Adopted by
National Quality Forum
as one of 30 US
"Safe Practices" (SP-15)
Notes: <number>
<number>
RED Checklist
Adopted by National Quality Forum as one of 30 US "Safe Practices" (SP-15)
Eleven mutually reinforcing components:
1. Medication reconciliation
2. Reconcile discharge plan with national guidelines
3. Follow-up appointments
4. Outstanding tests
5. Post-discharge services
6. Written discharge plan
7. What to do if problem arises
8. Patient education
9. Assess patient understanding
10. Discharge summary sent to PCP
11. Telephone reinforcement
<number>

## Slide 40: Project RED Components
Enable DA to:
Prepare patients for hospital discharge
Help patients safely transition from hospital to home
Promote patient self-health management
Support patients after discharge through follow-up phone call
Notes: <number>
Project RED Components
Enable DA to:
Prepare patients for hospital discharge
Help patients safely transition from hospital to home
Promote patient self-health management
Support patients after discharge through follow-up phone call
<number>

## Slide 41: Discharge Planning Rounds
Notes: Discharge Planning Rounds
Image: Physicians and administrators making rounds, taking notes, and collecting data.

## Slide 42: Generating the Discharge Care Plan
Manual – Use template for DA to enter all required data
Provide template to your IT Department and request that they integrate with existing systems
Purchas discharge planning software that is integrated with your existing systems
Notes: <number>
Generating the Discharge Care Plan
Manual – Use template for DA to enter all required data
Provide template to your IT Department and request that they integrate with existing systems
Purchas discharge planning software that is integrated with your existing systems

## Slide 43: AHRQ Template for Care Plan
Free, downloadable, fill-able PDF form
Based on Project RED After-Hospital Care Plan
Store on your server for easy access by DA
Integrate with your current systems as able
Hard copies available from AHRQ
www.ahrq.gov/qual/goinghomeguide.htm
Notes: AHRQ Template for Care Plan
Free, downloadable, fill-able PDF form
Based on Project RED After-Hospital Care Plan
Store on your server for easy access by DA
Integrate with your current systems as able
Hard copies available from AHRQ
www.ahrq.gov/qual/goinghomeguide.htm
Image: AHRQ Template for Care Plan booklet

## Slide 44
A Visual: After Hospital Care Plan http://www.bu.edu/fammed/projectred/toolkit.html
Notes: <number>
A Visual: After Hospital Care
http://www.bu.edu/fammed/projectred/toolkit.html
Image: Sample After Hospital Care Plan document

## Slide 45: Medications
Notes: <number>
Medications
Image: Graph of sample medications list for patient

## Slide 46: Medications - Continued
Notes: <number>
Medications – Continued
Image: Sample graph of medications for patient, color coded and time of day specific.

## Slide 47: Medications - Continued
Notes: <number>
Medications – Continued
Image: Sample graph of medications for patient, color coded and time of day specific

## Slide 48: Follow-up Appointments
Notes: <number>
Follow-up Appointments
Image: Sample document for follow up appointment schedule. Color coded and by date/time.

## Slide 49: Patient Questions
Notes: <number>
Patient Questions
Image: Sample template for patient questions and concerns to record and follow up on.

## Slide 50: Information About Condition
Notes: <number>
Information About Condition
Image: Sample "patient condition" information sheet.

## Slide 51: Location of Appointments
Notes: <number>
Location of Appointments
Image: Map of BMC Campus

## Slide 52: Compare Discharge Information
List current state
Patient name/diagnosis
List of DC medications
Review of prescriptions
Dietary recommendations
Activity limitations
Post DC appointment, if known
What are we missing?
RED Discharge Plan Components
Individual hard copy care plan (language specific)
Medication calendars in lay terms
Daily morning, afternoon, and evening meds identified
Patient questions list
Scheduled follow-up appointments
Pending tests and results
Location of appointments
Notes: Compare Discharge Information
List current state
Patient name/diagnosis
List of DC medications
Review of prescriptions
Dietary recommendations
Activity limitations
Post DC appointment, if known
What are we missing?
RED Discharge Plan Components
Individual hard copy care plan (language specific)
Medication calendars in lay terms
Daily morning, afternoon, and evening meds identified
Patient questions list
Scheduled follow-up appointments
Pending tests and results
Location of appointments
<number>

## Slide 53: Eliminate Documentation Time and Re-Writes
Ideally,
Information should flow from the medical record to the care provider who needs it
Information should flow from one practice setting to another
Information that is documented can be time stamped and assessed for accuracy
The discharge care plan could be automated and flow to the hands of the care team and patient
Notes: <number>
Eliminate Documentation Time and Re-Writes
Ideally,
Information should flow from the medical record to the care provider who needs it
Information should flow from one practice setting to another
Information that is documented can be time stamped and assessed for accuracy
The discharge care plan could be automated and flow to the hands of the care team and patient

## Slide 54: Poor Communication with PCP and Lack of Coordination
The hospital discharge process is often characterized by poor communication and a lack of coordination between the hospital and the PCP
When patients are discharged, they often do not know what medications their physicians have prescribed, when their follow-up appointments should take place, and, in some cases, why they were hospitalized
Notes: Poor Communication with PCP and Lack of Coordination
The hospital discharge process is often characterized by poor communication and a lack of coordination between the hospital and the PCP
When patients are discharged, they often do not know what medications their physicians have prescribed, when their follow-up appointments should take place, and, in some cases, why they were hospitalized

## Slide 55: Primary Care Physician Referral Base
Leaders will identify the PCP referral base
PCP satisfaction will be assessed prior to project launch
Physician champion will communicate with PCPs about project
PCPs will advise how to handle their off-shift and weekend patient needs
Notes: Primary Care Physician Referral Base
Leaders will identify the PCP referral base
PCP satisfaction will be assessed prior to project launch
Physician champion will communicate with PCPs about project
PCPs will advise how to handle their off-shift and weekend patient needs

## Slide 56: Post-Discharge Phone Call
Define who will call your patient after discharge
Define when the follow-up call will be made
Develop script for caller
Develop a process for off shifts and weekends
Notes: Post-Discharge Phone Call
Define who will call your patient after discharge
Define when the follow-up call will be made
Develop script for caller
Develop a process for off shifts and weekends

## Slide 57: Module 1: Summary Expected Outcomes
Align your strategic priorities
Develop an infrastructure that will promote communication, understanding of team progress, and documentation of the patient care plan
Review roles of executive sponsor, project team leader, DA, physician champion and pharmacist in the redesigned discharge process
Develop a systematic performance improvement process that will facilitate knowledge transfer and sustainable change
Embed Project RED key principles, including application of the Discharge Care Plan, communication with PCPs and implementing post DC phone calls
Notes: <number>
Module 1: Summary Expected Outcomes
Align your strategic priorities
Develop an infrastructure that will promote communication, understanding of team progress, and documentation of the patient care plan
Review roles of executive sponsor, project team leader, DA, physician champion and pharmacist in the redesigned discharge process
Develop a systematic performance improvement process that will facilitate knowledge transfer and sustainable change
Embed Project RED key principles, including application of the Discharge Care Plan, communication with PCPs and implementing post DC phone calls

## Slide 58: Progression to Module 2 Checklist
Before moving to Module 2:
Create your current state process map
Establish the primary physician referral base
Determine the Patient Care Plan structure
Initiate the project charter
Set dates for training frontline staff
Notes: Progression to Module 2 Checklist
Before moving to Module 2:
Create your current state process map
Establish the primary physician referral base
Determine the Patient Care Plan structure
Initiate the project charter
Set dates for training frontline staff