## Slide 1: Module 4
Re-Engineering Patient Discharge: The Hospital Launch
Notes: <number>
Module 4
Re-Engineering Patient Discharge: The Hospital Launch

## Slide 2: Accomplishments to Date (Module 1)
Process map of current discharge process completed
Primary care practitioner (PCP) referral base defined
Patient Care Plan structure finalized
Project charter initiated
Dates for training frontline staff set
Notes: <number>
Accomplishments to Date (Module 1)
Process map of current discharge process completed
Primary care practitioner (PCP) referral base defined
Patient Care Plan structure finalized
Project charter initiated
Dates for training frontline staff set

## Slide 3: Accomplishments to Date (Module 2)
Project metrics identified and planned
Patient inclusion criteria defined
Process for identifying patients and notifying Discharge Advocate defined
Multidisciplinary involvement and communication plan determined
Patient Care Plan process finalized (what data to include and how to gather it)
Notes: Accomplishments to Date (Module 2)
Project metrics identified and planned
Patient inclusion criteria defined
Process for identifying patients and notifying Discharge Advocate defined
Multidisciplinary involvement and communication plan determined
Patient Care Plan process finalized (what data to include and how to gather it)

## Slide 4: Accomplishments to Date (Module 3)
Processes to finalize Patient Care Plan after discharge order is written in place
Teach-back methods outlined
Quality and performance improvement (PI) staff understand project measurement requirements and are prepared to gather data
Process for transmitting discharge summary and Patient Care Plan to primary care physician finalized
Plans for teaching frontline staff finalized
Notes: <number>
Accomplishments to Date (Module 3)
Processes to finalize Patient Care Plan after discharge order is written in place
Teach-back methods outlined
Quality and performance improvement (PI) staff understand project measurement requirements and are prepared to gather data
Process for transmitting discharge summary and Patient Care Plan to primary care physician finalized
Plans for teaching frontline staff finalized

## Slide 5: Module 4 Objectives
Design an ideal future state process map
Finalize best practice solutions that include system redesign of the discharge process
Initiate the monitoring plan for sustainability
Celebrate staff accomplishments and discuss the application of the knowledge transfer framework across the hospital or system
Notes: Module 4 Objectives
Design an ideal future state process map
Finalize best practice solutions that include system redesign of the discharge process
Initiate the monitoring plan for sustainability
Celebrate staff accomplishments and discuss the application of the knowledge transfer framework across the hospital or system
<number>

## Slide 6: Module 4 Outline
Creating the ideal process map
Brainstorming improvements
Testing improvements
Creating the final deployment plan
Developing the monitoring plan
Planning the team celebration
Notes: Module 4 Outline
Creating the ideal process map
Brainstorming improvements
Testing improvements
Creating the final deployment plan
Developing the monitoring plan
Planning the team celebration

## Slide 7: Performance Improvement Structure
Deming, Shewhart, Lean
Plan
Do
Check (Study)
Act
Lean Six Sigma
Define
Measure
Analyze
Improve
Control
Notes: Performance Improvement Structure
Deming, Shewhart, Lean
Plan
Do
Check (Study)
Act
Lean Six Sigma
Define
Measure
Analyze
Improve
Control

## Slide 8: Your Current State May Have Looked Like This
Notes: Your Current State May Have Looked Like This
Image: Flow Chart of patient admission, care, and discharge process

## Slide 9
Notes: Sample Process Map: Patient Discharge
Image: Illustration of patient discharge process by profession – physician, nurse, pharmacy, DA
<number>

## Slide 10: Define Your Ideal Future State
Initiate a new high-level process map
Multidisciplinary participation
Patient admission is the starting point
After hospital care provision is the ending point
Ask each discipline what steps it will now take to prepare the patient for discharge
Notes: Define Your Ideal Future State
Initiate a new high-level process map
Multidisciplinary participation
Patient admission is the starting point
After hospital care provision is the ending point
Ask each discipline what steps it will now take to prepare the patient for discharge

## Slide 11
Notes: Sample Ideal State Project RED Flow Map
Image: Process map that outlines patient discharge process in the ideal state, identifying information and communication flow.
<number>

## Slide 12: Double Check for Failure Modes
Omission
Excessive repetition
Wrong sequence
Early or late execution
Incorrect identification or selection
Incorrect information
Incorrect counting or calculating
Overlooking
Misreading or misunderstanding
Incorrect decision
Incorrect transcription
Incorrect route, position, or setting
Notes: <number>
Double Check for Failure Modes
Omission
Excessive repetition
Wrong sequence
Early or late execution
Incorrect identification or selection
Incorrect information
Incorrect counting or calculating
Overlooking
Misreading or misunderstanding
Incorrect decision
Incorrect transcription
Incorrect route, position, or setting

## Slide 13: Current State Data Analysis
Collect baseline data from 5 to 10 patients, if possible
Analyze expected to actual time stamps (process metrics)
Analyze completed Patient Care Plans as defined
Analyze current state outcome metrics
Notes: Current State Data Analysis
Collect baseline data from 5 to 10 patients, if possible
Analyze expected to actual time stamps (process metrics)
Analyze completed Patient Care Plans as defined
Analyze current state outcome metrics
<number>

## Slide 14: Metrics for Target Population
Outcome metrics (readmission rate)
Financial metrics
Process metrics – time stamps
Process metrics – Patient Care Plan completion
Pre and post data – frontline staff, physicians, and patient surveys
Notes: Metrics for Target Population
Outcome metrics (readmission rate)
Financial metrics
Process metrics – time stamps
Process metrics – Patient Care Plan completion
Pre and post data – frontline staff, physicians, and patient surveys
<number>

## Slide 15: Check/Improve
Root causes of variation
Identified in Analyze step
Rank in relative importance
Brainstorm potential solutions for each root cause
Prioritize root causes with solutions
Notes: Check/Improve
Root causes of variation
Identified in Analyze step
Rank in relative importance
Brainstorm potential solutions for each root cause
Prioritize root causes with solutions
<number>

## Slide 16: Designing a Pilot Launch
Establish baseline performance
Train employees on pilot solution
Measure results of pilot solution
Analyze results of pilot solution
Decide to proceed to full-scale deployment
Notes: Designing a Pilot Launch
Establish baseline performance
Train employees on pilot solution
Measure results of pilot solution
Analyze results of pilot solution
Decide to proceed to full-scale deployment
<number>

## Slide 17: Deployment Planning
Review team mission and vision
Review strategic challenges
Align strategic objectives with action steps
Determine roles and goals
Establish communication plan
Align tactics with time horizons
Determine next steps
Notes: <number>
Deployment Planning
Review team mission and vision
Review strategic challenges
Align strategic objectives with action steps
Determine roles and goals
Establish communication plan
Align tactics with time horizons
Determine next steps

## Slide 18: Deployment Plan
Notes: Deployment Plan
Image: Sample graph template to map out deployment plan has columns for solution, tactical action step, responsibility, target date, and resources needed.
<number>

## Slide 19: Post-Implementation Data Collection
Collect data regularly
Seek help from quality department for data analysis
Notes: Post-Implementation Data Collection
Collect data regularly
Seek help from quality department for data analysis
<number>

## Slide 20: Survey Your Customer
Assess perceptions of
  Patients
  Frontline staff
  Primary care physicians
Analyze results
Notes: Survey Your Customer
Assess perceptions of
  Patients
  Frontline staff
  Primary care physicians
Analyze results
<number>

## Slide 21: Act/Control
Monitor pre- and post-project data
Define the monitoring plan for sustainability
Communicate results to the steering committee
Transfer knowledge to hospital staff and the community
Celebrate
Notes: Act/Control
Monitor pre- and post-project data
Define the monitoring plan for sustainability
Communicate results to the steering committee
Transfer knowledge to hospital staff and the community
Celebrate
<number>

## Slide 22: Executive Summary
Use updated project charter
Add pre- and post-project data
Note completed target dates
Notes: Executive Summary
Use updated project charter
Add pre- and post-project data
Note completed target dates

## Slide 23: Project Presentation to Senior Leaders
Create the presentation as you move through the PI project phases
Follow systematic PI methodology
Consider having team members present specific content
Link your presentation with an opportunity to recognize the team
Notes: Project Presentation to Senior Leaders
Create the presentation as you move through the PI project phases
Follow systematic PI methodology
Consider having team members present specific content
Link your presentation with an opportunity to recognize the team
<number>

## Slide 24: Planning Your Team Celebration
Celebrate team success
Cater to your team
Publicize
Personalize your thanks
Ask team members to share key lessons
Notes: Planning Your Team Celebration
Celebrate team success
Cater to your team
Publicize
Personalize your thanks
Ask team members to share key lessons
<number>

## Slide 25: Case Study
Preliminary interview to document expectations, concerns, perceived assets, and barriers
Intermediate interview to assess progress and actual versus expected experience
Final interview to document qualitative and quantitative impact
Notes: Case Study
Preliminary interview to document expectations, concerns, perceived assets, and barriers
Intermediate interview to assess progress and actual versus expected experience
Final interview to document qualitative and quantitative impact

## Slide 26: Qualitative Impact
Determine staff’s perception of:
  Project’s value compared with expectations
  Management support, patient impact, staff satisfaction, and overall quality
  Overall project
  Opportunities for improvement in dissemination
Notes: Qualitative Impact
Determine staff’s perception of:
  Project’s value compared with expectations
  Management support, patient impact, staff satisfaction, and overall quality
  Overall project
  Opportunities for improvement in dissemination

## Slide 27: Quantitative Impact
Outcome metrics
  Readmissions
  Patient satisfaction
  Patient compliance
  Medication errors after discharge
Process metrics
  Staff time spent on new process compared with old process
  Other process changes, such as calls to physicians, efficiency, etc.
Notes: Quantitative Impact
Outcome metrics
  Readmissions
  Patient satisfaction
  Patient compliance
  Medication errors after discharge
Process metrics
  Staff time spent on new process compared with old process
  Other process changes, such as calls to physicians, efficiency, etc.

## Slide 28: Module 4: Summary Expected Outcomes
Understanding of how to design an ideal future state process map
Understanding of best practice solutions that include system redesign of the discharge process
Understanding of how to initiate a monitoring plan for sustainability
Discussion of hospital-based case studies
Understanding of the importance of staff celebration and application of the knowledge transfer framework across the hospital or system
Notes: <number>
Module 4: Summary Expected Outcomes
Understanding of how to design an ideal future state process map
Understanding of best practice solutions that include system redesign of the discharge process
Understanding of how to initiate a monitoring plan for sustainability
Discussion of hospital-based case studies
Understanding of the importance of staff celebration and application of the knowledge transfer framework across the hospital or system

## Slide 29: Progression to Launch Checklist
___ Modules 1–3 deliverables accomplished
___ Ideal process map completed
___ Pilot test scheduled
___ Final deployment plan created
___ Case study presentation drafted
___ Project monitoring plan in place
Notes: Progression to Launch Checklist
___ Modules 1–3 deliverables accomplished
___ Ideal process map completed
___ Pilot test scheduled
___ Final deployment plan created
___ Case study presentation drafted
___ Project monitoring plan in place